## Reports
ISSUE DASHBOARDS
Scrolldown for the breakdown
|  | Escalated Issues |  | Resolved Issues
|  | 2023 | 0 | 2023 | 0 | 2024 | JAN | 22
|  | 2024 | 5 | 2024 | 92 | 2024 | FEB | 21
|  | 2025 |  | 2025 |  | 2024 | MAR | 21
Resolved Issues (This Year) | 92 | 2026 |  | 2026 |  | 2024 | APR | 20
Resolved Issues (Last Month) | 21 | 2027 |  | 2027 |  | 2024 | MAY | 8
Resolved Issues (This Month) | 21 | 2028 |  | 2028 |  | 2024 | JUN | 0
Resolved Issues (This Week) | 4 | 2029 |  | 2029 |  | 2024 | JUL | 0
Resolved Issues (Today) | 0 | 2030 |  | 2030 |  | 2024 | AUG | 0
Resolved Issues (Yesterday) | 1 | 2031 |  | 2031 |  | 2024 | SEP | 0
[6 empty] | 2024 | OCT | 0
Pending Tasks | 0 | TOTAL | 5 | TOTAL | 92 | 2024 | NOV | 0
[6 empty] | 2024 | DEC | 0
Counts Per Projects |  | Counts Per Type
Alpha | 27 | BUGS |  | 25
Beta | 27 | DATA |  | 37
Delta | 24 | OTHER |  | 16
Gamma | 22 | USER ERR |  | 22

## Tasks
Date Received | Date Resolved | Type | Project | Client | Description of the Issue | Solution | Progress
2024-01-01 | 2024-01-01 | DATA | Alpha | Emily | Login page not loading | Clear browser cache and cookies. | DONE
2024-01-02 | 2024-01-02 | BUGS | Delta | Jacob | Error message when submitting form | Update software to the latest version. | DONE
2024-01-03 | 2024-01-03 | USER ERR | Gamma | Ava | Missing data in database | Restart the application or device. | DONE
2024-01-04 | 2024-01-04 | DATA | Beta | Noah | Image upload not working | Check network connectivity and firewall settings. | DONE
2024-01-05 | 2024-01-05 | OTHER | Gamma | Olivia | Slow page load times | Verify data integrity in the database. | DONE
2024-01-06 | 2024-01-06 | BUGS | Alpha | Liam | Incorrect calculation in report | Reconfigure settings for better performance. | DONE
2024-01-09 | 2024-01-10 | USER ERR | Delta | Emma | Broken link on homepage | Contact customer support for assistance. | ESCALATED
2024-01-10 | 2024-01-10 | DATA | Beta | Jackson | Email notifications not sending | Reset password and security settings. | DONE
2024-01-11 | 2024-01-11 | DATA | Delta | Sophia | Popup window displaying error | Run antivirus scan for malware detection. | DONE
2024-01-12 | 2024-01-12 | BUGS | Alpha | Aiden | Mobile responsiveness issue | Optimize images and media files for faster loading. | DONE
2024-01-13 | 2024-01-13 | DATA | Gamma | Isabella | Page layout broken in Firefox | Implement SSL certificate for secure connections. | DONE
2024-01-16 | 2024-01-16 | OTHER | Beta | Lucas | Account activation link expired | Review and update content for accuracy. | DONE
2024-01-17 | 2024-01-17 | USER ERR | Gamma | Mia | Search function returning no results | Test website or application on different browsers. | DONE
2024-01-18 | 2024-01-18 | DATA | Alpha | Ethan | Payment gateway error during checkout | Monitor server resources and upgrade if needed. | DONE
2024-01-19 | 2024-01-19 | BUGS | Beta | Amelia | Dropdown menu not displaying options | Check for broken links and fix them. | DONE
2024-01-20 | 2024-01-20 | OTHER | Delta | James | Unauthorized access to admin panel | Backup and restore data from a recent backup. | DONE
2024-01-23 | 2024-01-23 | BUGS | Beta | Harper | Graph not updating with new data | Perform data validation and error handling. | DONE
2024-01-24 | 2024-01-24 | DATA | Gamma | Alexander | CSRF token validation failure | Implement CAPTCHA to prevent spam submissions. | DONE
2024-01-25 | 2024-01-25 | USER ERR | Delta | Charlotte | Incorrect date formatting | Review and update user permissions. | DONE
2024-01-26 | 2024-01-26 | DATA | Alpha | Michael | 404 error on specific page | Conduct user training for better usage understanding. | DONE
2024-01-27 | 2024-01-27 | BUGS | Gamma | Evelyn | SSL certificate expired | Optimize database queries for faster response. | DONE
2024-01-30 | 2024-01-30 | OTHER | Beta | Benjamin | Captcha code not displaying | Fix broken CSS or JavaScript code. | DONE
2024-01-31 | 2024-01-31 | USER ERR | Delta | Abigail | File upload size limit exceeded | Test forms and submission processes thoroughly. | DONE
2024-02-01 | 2024-02-01 | DATA | Gamma | Daniel | Broken video embed | Enable email notifications for critical alerts. | DONE
2024-02-02 | 2024-02-02 | BUGS | Alpha | Emily | Database connection timeout | Implement 301 redirects for outdated URLs. | DONE
2024-02-03 | 2024-02-03 | OTHER | Beta | Olivia | Currency conversion rate outdated | Configure caching settings for improved performance. | DONE
2024-02-06 | 2024-02-10 | USER ERR | Alpha | Alexander | Incorrect spelling in footer | Conduct usability testing for better user experience. | DONE
2024-02-07 | 2024-02-07 | DATA | Delta | Ethan | PDF download not working | Review and update website navigation. | DONE
2024-02-08 | 2024-02-08 | DATA | Beta | Ava | Password reset link not received | Install security patches and updates. | DONE
2024-02-09 | 2024-02-09 | BUGS | Gamma | Noah | Inconsistent font sizes across pages | Optimize page load times for better SEO. | DONE
2024-02-10 | 2024-02-10 | USER ERR | Delta | Amelia | Missing product images in catalog | Resolve DNS issues for domain connectivity. | DONE
2024-02-13 | 2024-02-13 | DATA | Beta | Sophia | Email attachment not opening | Implement content delivery network (CDN) for faster content delivery. | DONE
2024-02-14 | 2024-02-14 | BUGS | Gamma | Benjamin | Social media share buttons not visible | Review and update website design for modern look. | DONE
2024-02-15 | 2024-02-15 | OTHER | Alpha | Charlotte | Page freezing on scroll | Monitor server logs for error detection. | DONE
2024-02-16 | 2024-02-16 | USER ERR | Delta | Lucas | User permissions not applying correctly | Conduct A/B testing for website elements. | DONE
2024-02-17 | 2024-02-17 | DATA | Gamma | Mia | Error message during software update | Improve mobile responsiveness for various devices. | DONE
2024-02-20 | 2024-02-20 | BUGS | Beta | Aiden | Browser compatibility issue | Implement two-factor authentication for added security. | DONE
2024-02-21 | 2024-02-21 | DATA | Alpha | Harper | Data export feature not functioning | Conduct security audit and penetration testing. | DONE
2024-02-22 | 2024-02-22 | OTHER | Beta | Jacob | Website crashing under heavy traffic | Review and update privacy policy and terms of use. | DONE
2024-02-23 | 2024-02-23 | USER ERR | Delta | Isabella | Incorrect timezone display | Optimize database indexing for faster queries. | DONE
2024-02-24 | 2024-02-24 | BUGS | Alpha | Emily | Comment section not loading | Conduct regular backups and data archiving. | DONE
2024-02-27 | 2024-02-27 | DATA | Delta | Olivia | Broken slideshow on homepage | Update API integrations for better functionality. | DONE
2024-02-28 | 2024-02-28 | DATA | Gamma | Aiden | Cart items disappearing on checkout | Implement web analytics for data-driven insights. | DONE
2024-02-29 | 2024-02-29 | OTHER | Beta | Amelia | Mobile app crashing on launch | Fix broken redirects and canonical URLs. | DONE
2024-03-01 | 2024-03-01 | BUGS | Alpha | Jackson | Missing required fields in form | Test checkout process for smooth transactions. | DONE
2024-03-02 | 2024-03-02 | USER ERR | Beta | Harper | UI elements overlapping on mobile | Implement responsive images for different resolutions. | DONE
2024-03-05 | 2024-03-05 | DATA | Delta | Noah | Internal server error (500) | Review and update error messages for clarity. | DONE
2024-03-06 | 2024-03-06 | DATA | Gamma | Ava | Automated email sent to wrong recipient | Conduct performance testing for scalability. | DONE
2024-03-07 | 2024-03-07 | BUGS | Alpha | Alexander | Spam submissions in contact form | Optimize server configurations for resource efficiency. | DONE
2024-03-08 | 2024-03-08 | USER ERR | Beta | Charlotte | Outdated content on landing page | Fix broken image links and missing alt text. | DONE
2024-03-09 | 2024-03-09 | DATA | Gamma | Lucas | Image carousel not autoplaying | Update and validate SSL certificates. | DONE
2024-03-12 | 2024-03-12 | DATA | Delta | Mia | File upload progress bar not updating | Implement HTTPS for secure connections. | DONE
2024-03-13 | 2024-03-13 | OTHER | Gamma | Benjamin | Calendar event not syncing | Review and update content for SEO optimization. | DONE
2024-03-14 | 2024-03-14 | BUGS | Beta | Sophia | Product price display inconsistency | Fix JavaScript errors for better functionality. | DONE
2024-03-15 | 2024-03-15 | USER ERR | Alpha | Ethan | Database query returning error | Conduct load testing for website stability. | DONE
2024-03-16 | 2024-03-16 | DATA | Delta | Abigail | HTTPS mixed content warning | Implement email marketing automation. | DONE
2024-03-19 | 2024-03-19 | OTHER | Beta | Isabella | Malware detected on website | Optimize forms for better conversion rates. | DONE
2024-03-20 | 2024-03-20 | BUGS | Alpha | Jacob | Pop-up blocker preventing action | Review and update meta tags for search visibility. | DONE
2024-03-21 | 2024-03-22 | DATA | Alpha | Emily | Broken pagination links | Contact customer support for assistance. | ESCALATED
2024-03-22 | 2024-03-22 | USER ERR | Delta | Olivia | Menu dropdown not closing on click | Fix broken video embeds and media players. | DONE
2024-03-23 | 2024-03-23 | DATA | Beta | Alexander | Third-party API integration failure | Monitor website uptime and downtime. | DONE
2024-03-26 | 2024-03-26 | OTHER | Gamma | Amelia | Invalid username/password error | Optimize server response times for faster page loads. | DONE
2024-03-27 | 2024-03-27 | DATA | Alpha | Noah | Broken purchase link in email | Review and update social media integrations. | DONE
2024-03-28 | 2024-03-28 | BUGS | Delta | Ava | Slow response time on form submission | Conduct website accessibility testing. | DONE
2024-03-29 | 2024-03-29 | USER ERR | Gamma | Benjamin | Unresponsive support chat widget | Implement password policies for security. | DONE
2024-03-30 | 2024-03-30 | OTHER | Beta | Sophia | Incorrect billing information displayed | Fix broken links in sitemap. | DONE
2024-04-02 | 2024-04-02 | BUGS | Alpha | Aiden | Unclear error message for form validation | Review and update XML sitemap for search engines. | DONE
2024-04-03 | 2024-04-03 | DATA | Beta | Isabella | Database table corruption | Conduct keyword research for content optimization. | DONE
2024-04-04 | 2024-04-04 | USER ERR | Delta | Lucas | Broken RSS feed | Optimize image file sizes for faster loading. | DONE
2024-04-05 | 2024-04-05 | DATA | Gamma | Mia | Broken product link in email campaign | Implement lazy loading for images and videos. | DONE
2024-04-06 | 2024-04-06 | BUGS | Alpha | Harper | Server disk space exceeded | Fix broken RSS feed subscriptions. | DONE
2024-04-09 | 2024-04-09 | OTHER | Beta | Ethan | Unwanted characters in text input | Review and update meta descriptions for click-through rates. | DONE
2024-04-10 | 2024-04-10 | DATA | Alpha | Emily | Unsubscribed user still receiving emails | Conduct cross-browser testing for compatibility. | DONE
2024-04-11 | 2024-04-11 | USER ERR | Delta | Olivia | Database backup failure | Contact customer support for assistance. | ESCALATED
2024-04-12 | 2024-04-14 | DATA | Gamma | Alexander | Page title not updating dynamically | Implement geolocation features for personalized content. | DONE
2024-04-13 | 2024-04-13 | BUGS | Beta | Ava | Expired SSL certificate warning | Review and update content for relevance. | DONE
2024-04-16 | 2024-04-16 | DATA | Alpha | Noah | Automated cron job not running | Conduct website speed optimization. | DONE
2024-04-17 | 2024-04-17 | OTHER | Gamma | Amelia | Payment gateway refund error | Implement GDPR compliance for data protection. | DONE
2024-04-18 | 2024-04-18 | USER ERR | Delta | Sophia | Custom CSS not applying on page | Fix 404 errors and broken page links. | DONE
2024-04-19 | 2024-04-19 | BUGS | Beta | Benjamin | Website content loading out of order | Review and update contact forms for lead generation. | DONE
2024-04-20 | 2024-04-20 | DATA | Alpha | Charlotte | Broken URL redirection | Conduct security vulnerability assessments. | DONE
2024-04-23 | 2024-04-25 | USER ERR | Delta | Lucas | Unhandled JavaScript error | Optimize server configurations for peak traffic. | DONE
2024-04-24 | 2024-04-24 | DATA | Alpha | Mia | Payment gateway downtime | Implement email encryption for sensitive data. | DONE
2024-04-25 | 2024-04-25 | BUGS | Beta | Aiden | Image compression reducing quality | Fix broken navigation menus and dropdowns. | DONE
2024-04-26 | 2024-04-26 | OTHER | Delta | Isabella | Missing favicon on browser tab | Review and update blog content for engagement. | DONE
2024-04-27 | 2024-04-27 | USER ERR | Gamma | Jacob | Text alignment issues on mobile | Conduct server load balancing for high availability. | DONE
2024-04-30 | 2024-04-30 | DATA | Beta | Harper | Invalid link in email newsletter | Optimize page titles and headings for SEO. | DONE
2024-05-01 | 2024-05-02 | BUGS | Alpha | Emily | Corrupted PDF file download | Contact customer support for assistance. | ESCALATED
2024-05-02 | 2024-05-02 | DATA | Alpha | Olivia | Incorrect product stock status | Fix broken image galleries and slideshows. | DONE
2024-05-03 | 2024-05-03 | USER ERR | Delta | Alexander | Slow response from API endpoint | Review and update product descriptions for accuracy. | DONE
2024-05-04 | 2024-05-04 | DATA | Beta | Ava | Missing alt text for images | Conduct URL redirection audits. | DONE
2024-05-07 | 2024-05-07 | BUGS | Gamma | Noah | Broken order tracking link | Optimize server-side caching for performance. | DONE
2024-05-08 | 2024-05-08 | DATA | Delta | Amelia | SQL injection vulnerability detected | Implement content personalization for user experience. | DONE
2024-05-09 | 2024-05-09 | USER ERR | Alpha | Sophia | Data loss during form submission |  | IN PROG
2024-05-10 |  | OTHER | Beta | Benjamin | Incorrect language translation | Review and update email templates for branding. | DONE
2024-05-11 |  | BUGS | Alpha | Mia | Database query taking too long |  | IN PROG
2024-05-14 | 2024-05-14 | DATA | Delta | Lucas | Broken link in knowledge base article | Optimize server configurations for HTTPS. | DONE
2024-05-15 | 2024-05-15 | USER ERR | Beta | Aiden | Menu item leading to wrong page | Implement automatic software updates. | DONE
2024-05-16 | 2024-05-17 | DATA | Alpha | Isabella | Customer review not displaying | Contact customer support for assistance. | ESCALATED
2024-05-17 | 2024-05-17 | BUGS | Gamma | Harper | Email unsubscribe link not working | Review and update FAQ section for customer support. | DONE